## Slide 1: Change Order Procedure
Initiation
Project team identifies the need for a change. Complete the Change Order Request Form. Submit the request to the Project Manager.
Review
Project Manager reviews the request. Evaluate scope, cost, and impact on the schedule. Consult with relevant stakeholders.
Estimation
Obtain accurate cost estimates from suppliers and subcontractors. Include labor, materials, equipment, and potential schedule adjustments.
Approval
Project Manager seeks approval from the client. Client reviews the proposed change order. If approved, sign the Change Order Approval Form.
Documentation
Document all communication, approvals and issue related subcontractor change orders. Update project plans and drawings as needed. Ensure all team members are aware of the changes.
Monitoring
Monitor progress closely. Track actual costs against estimated costs. Adjust the project budget as necessary.
Completion
Verify that the change order work is complete. Confirm client satisfaction. Update project documentation for as-built records. Conduct a lessons learned review.
Validation
Negotiation
Execution