## How to Use This Sheet
How to Use This Sheet
Read the full tutorial: https://crewcost.com/blog/free-job-costing-template-construction
1. Create a budget or estimate for the job. Decide if you want to either break the job out into specific “products” or by line items for your schedule of values. If it’s a simpler job, you can also keep track of the budget without breaking it out. 2. Define your cost codes. Cost codes are unique numerical identifiers that help you keep track of specific costs within specific categories. This way, you can consistently allocate expenses across multiple jobs. Take a look at the sheet, “Job 10001” for a simple example of cost codes in action. Under the bigger category of Labor, you can see three cost codes that break out this category: Demo Labor, Install Labor, and Install Labor Overtime. Each one of these has a specific cost code associated with it. These cost codes make it easier to measure estimated vs. actual costs (something you’ll need to track overtime if you want to make more accurate estimates in future jobs). 3. Create a total for all the costs by type from your project budget. Once you have your total project budget, you’re going to break that down into the categories of Labor, Materials, Subcontract, Equipment, and Other. Take a look at the third template sheet “Job 10002” for a simple example. Here, the total project budget is broken down by floor, which is broken down further by labor, materials, subcontractors, and equipment. 4. Enter the entire budget amount for each cost type under the “Budget Amount” column. Now let’s start plugging in the numbers. Continuing with the previous example on the “Job 10002” sheet, let’s say you’ve allocated $25,020 for labor and $10,000 for materials for Floor One. You’ll add these amounts under the “Budget Amount” column. Once you’ve added all of the amounts for each floor, you should see your original budget for that specific job under the “TOTALS” line. 5. Record costs as they’re spent throughout the job. As you start to incur costs on the job, you’ll keep track of them in the “Cost to Date” cells. You’ll want to do this before you have your job cost meetings. Try to make this a monthly habit. When costs go up, you’ll see the “Forecast to Complete” number and “% Complete” numbers change. These columns are particularly important to keep an eye on. For instance, if your % Complete column shows 75% of your labor costs for Floor One have been spent, but only 50% of the work on the jobsite has been done, you know you’re potentially in for a budget overrun if you’re not careful. 6. Track change orders as needed. Need to put a change order in? Record it in the “Change Order” cell and add more change order cells as needed. This will create a “Revised Budget” for the line items affected. This revised budget will be the new number you’re using to complete the job. 7. Figure out your total revenue and profit. Once the job is done, you’ll record the total cost, along with your profit/markup to arrive at your total revenue. Check out our example on the first sheet, “Job ​​10000”.

## Job 10000
As of October 31, 2022
Job Name | Marriott HVAC Remodel | [6 empty] | Job Name | Marriott HVAC Remodel
Job Number | 10000 | [6 empty] | Job Number | 10000
[8 empty] | Cost Name | Cost Code | Cost Type | Hours/Number | Cost | Cost Code Total
Product
Cost Type | Budget Amount | Change Order | Revised Budget | Cost to Date | Forecast to Complete | % Complete | Over/Under | Elks Electric | 201-100 | Subcontract | 20 | 62.55 | 1251
Product - Electrical | 23448.25 | [6 empty] | Install Labor | 301-100 | Labor | 150 | 62.55 | 9382.5
Labor | 13448.25 | 4065.75 | 17514 | 13448.25 | 4065.75 | 76.79% |  | Install Labor - Overtime | 301-101 | Labor | 30 | 93.825 | 2814.75
Subcontractor | 10000 | 5000 | 15000 | 10000 | 5000 | 66.67% |  | Duct | 302-100 | Material | 1 | 5000 | 5000
[8 empty] | Handler | 302-100 | Material | 2 | 2500 | 5000
Area 2
Labor | 10633.5 | 0 | 10633.5 | 10633.5 | 0 | 100% |  | Area 2
Material | 9500 | 0 | 9500 | 9500 | 0 | 100% |  | Demo Labor | 201-100 | Labor | 15 | 62.55 | 938.25
[8 empty] | Install Labor | 301-100 | Labor | 125 | 62.55 | 7818.75
Area 3 | [7 empty] | Install Labor - Overtime | 301-101 | Labor | 20 | 93.825 | 1876.5
Labor | 15793.875 | 0 | 15793.875 | 15793.88 | -0.005 | 100% |  | Duct | 302-100 | Material | 1 | 4500 | 4500
Material | 10500 | 0 | 10500 | 10500 | 0 | 100% |  | Handler | 302-100 | Material | 2 | 2500 | 5000
Area 4 | [7 empty] | Area 3
Labor | 85068 | 0 | 85068 | 45000 | 40068 | 52.9% |  | Demo Labor | 201-100 | Labor | 25 | 62.55 | 1563.75
Materials | 65000 | 0 | 65000 | 32500 | 32500 | 50% |  | Install Labor | 301-100 | Labor | 175 | 62.55 | 10946.25
Subcontractor | 32000 | 0 | 32000 | 16000 | 16000 | 50% |  | Install Labor - Overtime | 301-101 | Labor | 35 | 93.825 | 3283.875
Equipment | 4125 | 0 | 4125 | 2075 | 2050 | 50.3% |  | Duct | 302-100 | Material | 1 | 5500 | 5500
[8 empty] | Handler | 302-100 | Material | 2 | 2500 | 5000
TOTALS | 256068.625 | 9065.75 | 265134.375 | 165450.63 | 99683.745 | 62.4%
Area 4
[8 empty] | Demo Labor | 201-100 | Labor | 125 | 62.55 | 7818.75
[8 empty] | Install Labor | 301-100 | Labor | 950 | 62.55 | 59422.5
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 190 | 93.825 | 17826.75
[8 empty] | 10 - 5 ton Units | 602-100 | Material | 10 | 6500 | 65000
[8 empty] | Controls | 702-100 | Subcontractor | 1 | 32000 | 32000
[8 empty] | Lift Rental | 602-200 | Equipment | 5 | 825 | 4125
[8 empty] | Total Labor Hours |  |  | 1860
[8 empty] | Total Cost |  |  |  |  | 256068.625
[8 empty] | Profit/Markup |  |  |  | 15% | 38410.2937
[8 empty] | Total Revenue |  |  |  |  | 294478.9188
[8 empty] | Job Name | Marriott HVAC Remodel
[8 empty] | Job Number | 10000
[8 empty] | Change Order | 1
[8 empty] | Description | Add one extra handler in Area 1
[8 empty] | Cost Name | Cost Code | Cost Type | Hours/Number | Cost | Cost Code Total
Area 1
[8 empty] | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 50 | 62.55 | 3127.5
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 10 | 93.825 | 938.25
[8 empty] | Duct | 302-100 | Material | 1 | 2500 | 2500
[8 empty] | Handler | 302-100 | Material | 1 | 2500 | 2500
Area 2
[8 empty] | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
[8 empty] | Duct | 302-100 | Material | 0 | 4500 | 0
[8 empty] | Handler | 302-100 | Material | 0 | 2500 | 0
Area 3
[8 empty] | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
[8 empty] | Duct | 302-100 | Material | 0 | 5500 | 0
[8 empty] | Handler | 302-100 | Material | 0 | 2500 | 0
Area 4
[8 empty] | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
[8 empty] | 10 - 5 ton Units | 602-100 | Material | 0 | 6500 | 0
[8 empty] | Controls | 702-100 | Subcontractor | 0 | 32000 | 0
[8 empty] | Lift Rental | 602-200 | Equipment | 0 | 825 | 0
[8 empty] | Total Labor Hours |  |  | 60
[8 empty] | Total Cost |  |  |  |  | 9065.75
[8 empty] | Profit/Markup |  |  |  | 15% | 1359.8625
[8 empty] | Total Revenue |  |  |  |  | 10425.6125

## Job 10001
Job Name | Academy HVAC Remodel | [6 empty] | Job Name | Academy HVAC Remodel
Job Number | 10001 | [6 empty] | Job Number | 10001
[8 empty] | Cost Name | Cost Code | Cost Type | Hours/Number | Cost | Cost Code Total
Cost Type | Budget Amount | Change Order | Revised Budget | Cost to Date | Forecast to Complete | % Complete | Over/Under | Demo Labor | 201-100 | Labor | 130 | 62.55 | 8131.5
Labor | 87413.625 | 0 | 87413.625 | 35000 | 52413.625 | 40.04% |  | Install Labor | 301-100 | Labor | 975 | 62.55 | 60986.25
Material | 51500 | 0 | 51500 | 44000 | 7500 | 85.44% |  | Install Labor - Overtime | 301-101 | Labor | 195 | 93.825 | 18295.875
Subcontractor | 18000 | 0 | 18000 | 3000 | 15000 | 16.67% |  | Duct | 302-100 | Material | 3 | 2500 | 7500
Equipment | 3300 | 0 | 3300 | 1500 | 1800 | 45.45% |  | Handler | 302-100 | Material | 4 | 2500 | 10000
Other | 1500 | 0 | 1500 | 250 | 1250 | 16.67% |  | 8 - 3.5 ton Units | 602-100 | Material | 8 | 4250 | 34000
[8 empty] | Controls | 702-100 | Subcontractor | 1 | 18000 | 18000
TOTALS | 161713.625 | 0 | 161713.625 | 83750 | 77963.625 | 51.79% |  | Lift Rental | 602-200 | Equipment | 4 | 825 | 3300
[8 empty] | Safety Consultant | 802-100 | Other | 1 | 1500 | 1500
[8 empty] | Total Labor Hours |  |  | 1300
[8 empty] | Total Cost |  |  |  |  | 161713.625
[8 empty] | Profit/Markup |  |  |  | 15% | 24257.0438
[8 empty] | Total Revenue |  |  |  |  | 185970.6688

## Job 10002
Job Name | HEB New Building | [6 empty] | Job Name | HEB New Building
Job Number | 10002 | [6 empty] | Job Number | 10002
[8 empty] | Cost Name | Cost Code | Cost Type | Hours/Number | Cost | Cost Code Total
Floor 1
Cost Code Name | Budget Amount | Change Order | Revised Budget | Cost to Date | Forecast to Complete | % Complete | Over/Under | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
Floor 1 | [7 empty] | Install Labor | 301-100 | Labor | 400 | 62.55 | 25020
Labor | 25020 | 0 | 25020 | 13448.25 | 11571.75 | 53.75% |  | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
Material | 10000 | 0 | 10000 | 10000 | 0 | 100% |  | Duct | 302-100 | Material | 1 | 5000 | 5000
[8 empty] | Handler | 302-100 | Material | 2 | 2500 | 5000
Floor 2
Labor | 31275 | 0 | 31275 | 15025 | 16250 | 48.04% |  | Floor 2
Material | 9500 | 0 | 9500 | 9500 | 0 | 100% |  | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 500 | 62.55 | 31275
Floor 3 | [7 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
Labor | 25020 | 0 | 25020 | 15793.88 | 9226.12 | 63.13% |  | Duct | 302-100 | Material | 1 | 4500 | 4500
Material | 10500 | 0 | 10500 | 10500 | 0 | 100% |  | Handler | 302-100 | Material | 2 | 2500 | 5000
Floor 4 | [7 empty] | Floor 3
Labor | 39093.75 | 0 | 39093.75 | 24000 | 15093.75 | 61.39% |  | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
Material | 10500 | 0 | 10500 | 10500 | 0 | 100% |  | Install Labor | 301-100 | Labor | 400 | 62.55 | 25020
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
Roof | [7 empty] | Duct | 302-100 | Material | 1 | 5500 | 5500
Labor | 218925 | 0 | 218925 | 92500 | 126425 | 42.25% |  | Handler | 302-100 | Material | 2 | 2500 | 5000
Materials | 310000 | 0 | 310000 | 290000 | 20000 | 93.55%
Subcontractor | 85000 | 0 | 85000 | 62500 | 22500 | 73.53% |  | Floor 4
Equipment | 12375 | 0 | 12375 | 2075 | 10300 | 16.77% |  | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 625 | 62.55 | 39093.75
TOTALS | 787208.75 | 0 | 787208.75 | 555842.13 | 231366.62 | 70.61% |  | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
[8 empty] | Duct | 302-100 | Material | 1 | 5500 | 5500
[8 empty] | Handler | 302-100 | Material | 2 | 2500 | 5000
Roof
[8 empty] | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 3500 | 62.55 | 218925
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
[8 empty] | 4 - 30 ton Units | 602-100 | Material | 4 | 72500 | 290000
[8 empty] | Controls | 702-100 | Subcontractor | 1 | 85000 | 85000
[8 empty] | Lift Rental | 602-200 | Equipment | 15 | 825 | 12375
[8 empty] | Duct | 302-100 | Material | 1 | 20000 | 20000
[8 empty] | Total Labor Hours |  |  | 5425
[8 empty] | Total Cost |  |  |  |  | 787208.75
[8 empty] | Profit/Markup |  |  |  | 15% | 118081.3125
[8 empty] | Total Revenue |  |  |  |  | 905290.0625

## Job 10003
Job Name | Google building HVAC Remodel | [6 empty] | Job Name | Google building HVAC Remodel
Job Number | 10003 | [6 empty] | Job Number | 10003
[8 empty] | Cost Name | Cost Code | Cost Type | Hours/Number | Cost | Cost Code Total
Cost Code Name | Budget Amount | Change Order | Revised Budget | Cost to Date | Forecast to Complete | % Complete | Over/Under | Demo Labor | 201-100 | Labor | 450 | 62.55 | 28147.5
Labor | 189995.625 | 0 | 189995.625 | 35000 | 154995.625 | 18.42% |  | Install Labor | 301-100 | Labor | 2250 | 62.55 | 140737.5
Material | 467500 | 0 | 467500 | 77000 | 390500 | 16.47% |  | Install Labor - Overtime | 301-101 | Labor | 225 | 93.825 | 21110.625
Subcontractor | 195000 | 0 | 195000 | 3000 | 192000 | 1.538% |  | Duct | 302-100 | Material | 15 | 2500 | 37500
Equipment | 12375 | 0 | 12375 | 1500 | 10875 | 12.12% |  | Handler | 302-100 | Material | 12 | 2500 | 30000
Other | 10000 | 0 | 10000 | 250 | 9750 | 2.5% |  | 8 - 30 ton Units | 602-100 | Material | 8 | 50000 | 400000
[8 empty] | Controls | 702-100 | Subcontractor | 1 | 120000 | 120000
TOTALS | 874870.625 | 0 | 874870.625 | 116750 | 758120.625 | 13.34% |  | Lift Rental | 602-200 | Equipment | 15 | 825 | 12375
[8 empty] | Safety Consultant | 802-100 | Other | 1 | 10000 | 10000
[8 empty] | Crane | 702-100 | Subcontractor | 1 | 75000 | 75000
[8 empty] | Total Labor Hours |  |  | 2925
[8 empty] | Total Cost |  |  |  |  | 874870.625
[8 empty] | Profit/Markup |  |  |  | 15% | 131230.5938
[8 empty] | Total Revenue |  |  |  |  | 1006101.219

## Job 10005
Job Name | Indeed Building Remodel | [6 empty] | Job Name | Indeed Building Remodel
Job Number | 10005 | [6 empty] | Job Number | 10005
[8 empty] | Cost Name | Cost Code | Cost Type | Hours/Number | Cost | Cost Code Total
Cost Code Name | Budget Amount | Change Order | Revised Budget | Cost to Date | Forecast to Complete | % Complete | Over/Under | Demo Labor | 201-100 | Labor | 350 | 62.55 | 21892.5
[8 empty] | Install Labor | 301-100 | Labor | 2500 | 62.55 | 156375
Labor | 201723.75 | 0 | 201723.75 | 0 | 201723.75 | 0% |  | Install Labor - Overtime | 301-101 | Labor | 250 | 93.825 | 23456.25
Material | 337500 | 0 | 337500 | 0 | 337500 | 0% |  | Duct | 302-100 | Material | 20 | 2500 | 50000
Subcontractor | 130000 | 0 | 130000 | 15000 | 115000 | 11.54% |  | Handler | 302-100 | Material | 15 | 2500 | 37500
Equipment | 9900 | 0 | 9900 | 0 | 9900 | 0% |  | 8 - 30 ton Units | 602-100 | Material | 5 | 50000 | 250000
Other | 12520 | 0 | 12520 | 0 | 12520 | 0% |  | Controls | 702-100 | Subcontractor | 1 | 68000 | 68000
[8 empty] | Lift Rental | 602-200 | Equipment | 12 | 825 | 9900
TOTALS | 691643.75 | 0 | 691643.75 | 15000 | 676643.75 | 2.169% |  | Safety Consultant | 802-100 | Other | 1 | 12520 | 12520
[8 empty] | Crane | 702-100 | Subcontractor | 1 | 62000 | 62000
[8 empty] | Total Labor Hours |  |  | 3100
[8 empty] | Total Cost |  |  |  |  | 691643.75
[8 empty] | Profit/Markup |  |  |  | 25% | 172910.9375
[8 empty] | Total Revenue |  |  |  |  | 864554.6875

## Job 10004
Job Name | Hilton New Buildout | [6 empty] | Job Name | Hilton New Buildout
Job Number | 10004 | [6 empty] | Job Number | 10004
[8 empty] | Cost Name | Cost Code | Cost Type | Hours/Number | Cost | Cost Code Total
Front Desk
Cost Code Name | Budget Amount | Change Order | Revised Budget | Cost to Date | Forecast to Complete | % Complete | Over/Under | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
Front Desk | [7 empty] | Install Labor | 301-100 | Labor | 50 | 62.55 | 3127.5
Labor | 3127.5 | 0 | 3127.5 | 3127.5 | 0 | 100% |  | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
Material | 7500 | 0 | 7500 | 7500 | 0 | 100% |  | Duct | 302-100 | Material | 1 | 5000 | 5000
[8 empty] | Handler | 302-100 | Material | 1 | 2500 | 2500
Conference Rooms
Labor | 46912.5 | 0 | 46912.5 | 0 | 46912.5 | 0% |  | Conference Rooms
Material | 57500 | 0 | 57500 | 0 | 57500 | 0% |  | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 750 | 62.55 | 46912.5
Kitchen | [7 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
Labor | 18765 | 0 | 18765 | 0 | 18765 | 0% |  | Duct | 302-100 | Material | 10 | 4500 | 45000
Material | 16000 | 0 | 16000 | 0 | 16000 | 0% |  | Handler | 302-100 | Material | 5 | 2500 | 12500
0
Roof | [7 empty] | Kitchen
Labor | 62550 | 0 | 62550 | 0 | 62550 | 0% |  | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
Materials | 65000 | 0 | 65000 | 0 | 65000 | 0% |  | Install Labor | 301-100 | Labor | 300 | 62.55 | 18765
Subcontractor | 50000 | 0 | 50000 | 37000 | 13000 | 74% |  | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
Equipment | 4125 | 0 | 4125 | 0 | 4125 | 0% |  | Duct | 302-100 | Material | 2 | 5500 | 11000
[8 empty] | Handler | 302-100 | Material | 2 | 2500 | 5000
TOTALS | 331480 | 0 | 331480 | 47627.5 | 283852.5 | 14.37%
Roof
[8 empty] | Demo Labor | 201-100 | Labor | 0 | 62.55 | 0
[8 empty] | Install Labor | 301-100 | Labor | 1000 | 62.55 | 62550
[8 empty] | Install Labor - Overtime | 301-101 | Labor | 0 | 93.825 | 0
[8 empty] | 10 - 5 ton Units | 602-100 | Material | 10 | 6500 | 65000
[8 empty] | Controls | 702-100 | Subcontractor | 1 | 35000 | 35000
[8 empty] | Lift Rental | 602-200 | Equipment | 5 | 825 | 4125
[8 empty] | Crane | 702-100 | Subcontractor | 1 | 15000 | 15000
[8 empty] | Total Labor Hours |  |  | 2100
[8 empty] | Total Cost |  |  |  |  | 331480
[8 empty] | Profit/Markup |  |  |  | 20% | 66296
[8 empty] | Total Revenue |  |  |  |  | 397776