## Template
SCHEDULE OF VALUES
Job No. |  |  |  |  | Application No.
Project No. |  |  |  |  | Application Date
Contractor |  |  |  |  | Period to
Item # | Description of Work | Scheduled Value | WORK COMPLETED |  | Stored Materials (not in D or E) | Total Completed & Stored to Date | % Complete | Balance to Finish | Retainage*
|  |  | Previous Application | This Period |  |  |  |  | 10%
9970 | Demolition | 3000 | 2000 | 0 | 0 | 2000 | 0.66667 | 1000 | 200
9955 | Drywall & Carpentry | 36000 | 11000 | 4200 | 1800 | 17000 | 0.47222 | 19000 | 1700
9940 | Doors & Hardware | 1000 | 0 | 500 | 0 | 500 | 0.5 | 500 | 50
9943 | Electrical | 7000 | 1000 | 3000 | 850 | 4850 | 0.69286 | 2150 | 485
Totals |  | 47000 | 14000 | 7700 | 2650 | 24350 | 0.51809 | 22650 | 2435